## Project Status
PROJECT STATUS REPORT
Project Name: | Enter project name |  | Reporting Period: | Week ending
Overall Status | Green / Amber / Red
Headline | One-line summary of where the project stands
Area | Status | Last Week | This Week | Owner | Notes
Schedule | Green | On track | On track | PM | Milestone dates unchanged
Budget | Amber | Within 5% | Within 7% | PMO | Supplier invoice pending
Scope | Green | Baseline | Baseline | PM | No change requests
Risk | Amber | 3 open | 4 open | Risk Lead | New dependency risk
Resources | Green | Allocated | Allocated | Resource Mgr | Team complete

## Portfolio Dashboard
PORTFOLIO DASHBOARD
Portfolio: | Enter portfolio name |  | Date: | YYYY-MM-DD
Project | Phase | Status | Budget | Forecast | Risks | Next Gate
Project Alpha | Execution | Green | $500K | $495K | 2 | Q2 Review
Project Beta | Planning | Amber | $300K | $310K | 4 | Kick-off
Project Gamma | Close-out | Green | $200K | $198K | 1 | Benefits review

## Executive Summary
EXECUTIVE SUMMARY
Reporting Period: | Month / Quarter
Strategic Confidence | Green / Amber / Red
Key Message | One paragraph on whether the portfolio is delivering the strategy
Theme | Status | Trend | Key Metric | Decision Needed
Digital transformation | Amber | ↓ | 62% on target | Approve additional budget
Customer platform | Green | → | Live in 3 markets | None
Cost reduction | Green | ↑ | $2.1M saved | Roll out to APAC

## RAID Log
RAID LOG
ID | Description | Type | Impact | Owner | Status
R01 | Supplier delivery delay | Risk | High | Procurement | Open
A01 | API rate limits assumed | Assumption | Medium | Tech Lead | Monitoring
I01 | Budget approval pending | Issue | High | PMO | Escalated
D01 | Legal sign-off required | Dependency | Medium | Legal | In Progress

## Milestone Tracker
MILESTONE TRACKER
Milestone | Baseline Date | Forecast Date | Status | Notes
Requirements signed off | 2026-01-15 | 2026-01-15 | Complete | All stakeholders approved
Design complete | 2026-02-28 | 2026-03-05 | At risk | UI review delayed
Pilot launch | 2026-04-15 | 2026-04-15 | On track | Training scheduled
Go-live | 2026-06-01 | 2026-06-08 | Amber | Contingency built in